# Gantt Chart for Research project – Colour Coded with Milestones

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  |  |  |
| Week Numbers (Timeline) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |
| Topic selection and supervisor allocation | █ | █ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Preliminary literature review |  | █ | █ | █ | █ | █ | █ | █ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Drafting research objectives & aims |  |  |  | █ | █ | █ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Research proposal draft writing |  |  |  |  |  |  | █ | █ | █ | █ | █ | █ | █ |  |  |  |  |  |  |  |  |  |  |
| Reading methodology |  |  |  |  |  |  |  | █ | █ | █ | █ |  |  |  |  |  |  |  |  |  |  |  |  |
| Proposal submission and feedback (Milestone) |  |  |  |  |  |  |  |  |  |  | █ | █ | █ | █ |  |  |  |  |  |  |  |  |  |
| Extended literature review and reading |  |  |  |  |  |  |  |  | █ | █ | █ | █ | █ |  |  |  |  |  |  |  |  |  |  |
| Research methodology design |  |  |  |  |  |  |  |  |  |  |  |  | █ | █ | █ | █ | █ |  |  |  |  |  |  |
| Ethical review and approval and questionnaire preparation |  |  |  |  |  |  |  |  |  |  |  | █ | █ | █ | █ | █ |  |  |  |  |  |  |  |
| Data collection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | █ | █ | █ | █ | █ | █ | █ |
| Data cleaning and analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  | █ | █ | █ | █ | █ | █ | █ | █ | █ |
| Drafting findings and discussion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Writing introduction and conclusion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Proofreading and final editing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final submission preparation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submission of report (Milestone) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |